DPC’s 
Gender Equality 
Action Plan 
2021–2025

Accessible

Authorised and published by the Victorian Government

1 Treasury Place, Melbourne

Gender Equality Action Plan 2021–2025

March 2022

© Copyright State Government of Victoria 2022

This publication is copyright. No part may be reproduced by any process except in accordance with provisions of the Copyright Act 1968.

For an accessible version of this publication, visit the DPC website <https://www.vic.gov.au/dpc-governance-and-reporting>.

Acknowledgement of Country

The Department of Premier and Cabinet (DPC) proudly acknowledges Victoria’s First Nations peoples and their ongoing strength in practising the world’s oldest living culture. We acknowledge the Traditional Custodians of Country throughout Victoria and pay our respects to their cultures and Elders past, present and emerging.

Message from the Secretary	4

Message from the Gender Equality Champion	5

1.	Our vision	6

Legislative Framework: Gender Equality Act 2020	6

Gender Equality Action Plan 2021 – 2025	7

2.	Strategic context	8

3.	Building on achievements under the Gender Equality Action Plan 2018–2021	9

4.	How we developed this Gender Equality Action Plan	10

Gender Equality data analysis	10

Consultation with stakeholders	10

Intersectionality	11

5.	Key actions	12

Action areas	12

Action Area 1: Visible leadership and accountability	13

Action Area 2: Reducing the gender pay gap	15

Action Area 3: Attracting, developing, and retaining a gender balanced and talented workforce	16

Action Area 4: Creating a safe, respectful, and inclusive workplace	18

Action Area 5: Facilitating and promoting a flexible workplace	20

Action Area 6: Measuring, monitoring, and reporting on gender equality	22

6.	Leadership and resourcing	23

Leadership and governance	23

Governance and resourcing	23

7.	Measuring progress and reporting	24

Measuring progress	24

Reporting	24

Implementation	24

Attachment A: Analysing Gender Equality at DPC	25

Key findings and insights	25

## Message from the Secretary

The Department of Premier and Cabinet’s (DPC) Gender Equality Action Plan 2021-2025 (the Plan) provides us with a clear pathway for establishing a fair and respectful workplace for all staff.

As a central agency within the Victorian Public Service, our department has an opportunity to be a leader in promoting gender equality in every facet of what we do, including – but not limited to – considering how pay and conditions, recruitment policies, and career development can impact women differently and what we can do to remedy inequality.

This Plan commits DPC to new and achievable objectives for the next four years. As we transition to a hybrid working model that supports flexibility and gives staff greater autonomy over how they structure their professional lives, the DPC Board of Management are committed to working with you to deliver the changes needed.

As a member of the Champions of Change Coalition, I also commit to working with leaders across government and industry to accelerate progress and deliver critical reforms.

The vision and actions set out here are a credit to the work of the Gender Equality Working Group, and the critical contributions from the DPC Enablers Network, Aboriginal Staff Network, LGBTIQ+ Network and VPS5 Network. In many cases, a person experiencing one inequality or disadvantage will also be experiencing another, so it is important such a diverse group of staff have had their voices heard. The comprehensive research underpinning this plan will ensure that it meets the values and expectations of our workforce, while also meeting our obligations under the Gender Equality Act 2020.

I encourage all of you to read this Plan, reflect upon its findings and action items, and take proactive steps in your own work towards building a stronger and more diverse DPC.

Jeremi Moule
Secretary

## Message from the Gender Equality Champion

I am pleased to introduce the Department of Premier and Cabinet’s (DPC) Gender Equality Action Plan 2021–2025. This plan lays the foundation for a range of work over the next four years to ensure everyone at DPC, including women and gender diverse staff, has safe and equal access to resources, opportunities, and leadership roles, and is always treated with dignity, respect, and fairness.

The social, economic and productivity benefits of gender equality are experienced by everyone. In workplaces, gender equality leads to improvements in organisational performance, employee engagement and wellbeing and the attraction and retention of talent and staff.

This plan builds on the success of our previous Gender Equality Action Plan 2018–2021, through which we introduced additional paid parental leave for secondary carers, developed a policy to support those affected by family or domestic violence, instituted a program support to employees as they become parents and then become working parents, and ensured at least half of our executive roles are filled by women. These were all major achievements that represented hugely positive steps towards gender equality.

This new Plan renews our focus. Over the next four years, we commit to:

recruiting and retaining a diverse, gender-balanced workforce

supporting the career advancement of women, including into leadership roles

growing a safe, respectful, and inclusive workplace

reducing the gender pay gap

encouraging flexible / new ways of working and

supporting employees to balance work, family, and caring responsibilities.

I encourage all DPC staff to take up the challenge set by this plan and discover what opportunities are out there for you and your peers. It is within everyone’s remit to make DPC a more safe, more inclusive, and more equitable workplace.

Vivien Allimonos
Deputy Secretary, Cabinet, Communications and Corporate
DPC Executive Champion for Gender Equality

## Our vision

The Department of Premier and Cabinet (the department/DPC) values the diversity of our workforce and is committed to the principles of diversity, inclusion, and equality, so that all our employees, including women and gender diverse staff, have equal access to employment opportunities and outcomes. We are committed to taking positive action towards achieving workplace gender equality and have developed the Gender Equality Action Plan 2021–2025 (the Plan) in partnership with our people to acknowledge and reflect on the challenges and opportunities to achieve gender equality.

Our vision for DPC is a safe, inclusive, and equitable workplace where all staff, irrespective of gender, have the opportunity to reach their full potential.

While DPC has made considerable progress in creating a gender balanced, flexible and inclusive workplace, our current workforce data indicates that despite the gender composition of our workforce being 61 per cent women, workplace gender inequality persists. A gender pay gap exists, in part due to the concentration of men within the more senior executive bands compared to women, and due to a degree of occupational segregation, where a higher proportion of women are employed at the VPS 1-5 level.

Our 2021 People Matter Survey measures also highlight opportunities for improvement to support women to reach their full potential at DPC. Women responded less favourably to questions about flexible working, family/caring responsibilities, and opportunities for promotion. Women also reported experiencing inappropriate workplace behaviours such as bullying, and violence or aggression at a higher rate than men.

We also acknowledge that we live in a society in which, despite considerable progress, women continue to experience inequality and discrimination in the workplace which limits the opportunities available to them. DPC supports the Victorian Government vision for gender equality under Safe and Strong, Victoria’s Gender Equality Strategy – that all Victorians live in a safe and equal society, have access to equal power, resources and opportunities and are treated with dignity, respect, and fairness. We understand that gender inequality may also be compounded by other forms of disadvantage or discrimination that a person may experience on the basis of their Aboriginality, age, disability, ethnicity, gender identity, race, religion, sexual orientation, and other attributes. The experience of compounding or overlapping forms of disadvantage or discrimination is referred to as intersectionality.1

In developing the Plan, DPC demonstrates our strong commitment to gender equality, in particular to providing equal pay for work of equal or comparable value, removing barriers to the equal representation and participation of women in the workplace, offering access to career development opportunities and promotion, including into leadership and non-traditional roles, and providing a flexible, safe, and inclusive workplace.

### Legislative Framework: Gender Equality Act 2020

The Gender Equality Act 2020 (the Act) commenced on 31 March 2021, requiring defined entities to take positive action towards achieving workplace gender equality and to promote gender equality in their policies, programs, and services. Under the Act, DPC is required to:

develop and implement a Gender Equality Action Plan

promote gender equality in policies, programs and services that impact the public

publicly report on progress in relation to workplace gender equality

complete gender impact assessments.

The Act also enshrines a number of gender equality principles:

All Victorians should live in a safe and equal society, have access to equal power, resources and opportunities and be treated with dignity, respect, and fairness.

Gender equality benefits all Victorians regardless of gender.

Gender equality is a human right and precondition to social justice.

Gender equality brings significant economic, social and health benefits for Victoria.

Gender equality is a precondition for the prevention of family violence and other forms of violence against women and girls.

Advancing gender equality is a shared responsibility across the Victorian community.

All human beings, regardless of gender, should be free to develop their personal abilities, pursue their professional careers and make choices about their lives without being limited by gender stereotypes, gender roles or prejudices.

Gender inequality may be compounded by other forms of disadvantage or discrimination that a person may experience on the basis of Aboriginality, age, disability, ethnicity, gender identity, race, religion, sexual orientation, and other attributes.

Women have historically experienced discrimination and disadvantage on the basis of sex and gender.

Special measures may be necessary to achieve gender equality.

### Gender Equality Action Plan 2021 – 2025

As part of our commitment to gender equality and under the guidance of the Commission for Gender Equality in the Public Sector, DPC has now developed our Gender Equality Action Plan, which is guided by the results of a comprehensive workplace gender audit and consultation with a variety of stakeholders to develop evidence-based strategies for achieving workplace gender equality over the next four years.

## Strategic context

DPC has developed a number of individual action plans that sit under our Diversity and Inclusion Strategy 2019–2021, which has five priority areas:

Gender equality

Aboriginal workforce

Disability access and inclusion

LGBTIQ+ inclusion

Cultural and linguistically diverse (CALD) inclusion

The following diagram shows where the Plan fits into the internal diversity and inclusion framework and how our focus on gender equality complements existing organisational strategies. The diagram also identifies the relevant legislation standards and guidelines considered in developing this plan.

A number of strategies contained in the Plan align with the measures outlined in the individual action plans relating to People with Disability and DPC’s Aboriginal, LGBTIQ+, and CALD workforce. The individual plans however contain more focussed strategies to address gender inequality specific to the experiences of each group.

#### Diversity and Inclusion Strategy

Gender Equality Action Plan 2021–2025

Gender Equality Act 2020 (Vic)

Workplace Gender Equality Act 2012 (Cwlth)

Sex Discrimination Act 1984 (Cwlth)

Fair Work Act 2009 (Cwlth)

Equal Opportunity Act 2010 (Vic)

Charter of Human Rights and Responsibilities Act 2006 (Vic)

Victorian Public Service Enterprise Agreement 2020

Safe and Strong, A Victorian Gender Equality Strategy 2016

Aboriginal Workforce Strategy 2022–2026 (in development)

Disability Access and Inclusion Plan 2021–2025

LGBTIQ+ Inclusion Plan (for review)

Cultural Diversity Plan (for review)

## Building on achievements under the Gender Equality Action Plan 2018–2021

The development of the Plan provides DPC an opportunity to build on progress made towards achieving gender equality over the period 2018-2021, during which DPC delivered several initiatives to improve gender equality in the workplace:

Maintained and exceeded the overall target of 50 per cent of women in Executive roles.

Developed a Family Violence Support policy outlining workplace support available to employees experiencing or impacted by family violence.

Delivered mandatory family violence training for all managers and Executives and created the role of Family Violence Contact Officers.

Implemented the Parental Transition Support Program which offers specialist coaching and on-line assistance to support the transition from worker, to parent, to working parent.

Implemented a new entitlement of 12 weeks paid parental leave for secondary carers in addition to the four weeks of paid parental leave already available, under the provisions of the VPS Enterprise Agreement 2020.

Implemented the DPC In Touch program to support women on parental leave to maintain contact and relationships with managers and peers.

Updated the Prevention of Sexual Harassment in the Workplace policy and mandatory eLearning module.

Continued to support career development for women by participating in and nominating women for leadership programs.

Developed a Flexible Working policy and form to capture and monitor the uptake of formal flexible working arrangements.

Completed a comprehensive workplace gender audit to inform the development of the Gender Equality Action Plan 2021-2025.

Continued membership and participation in the Champions of Change Coalition, a global initiative in which men of power step up beside women leaders as ‘champions’ because they publicly commit to leading practical, constructive and disruptive actions to accelerate change to achieve gender equality and build respectful and inclusive workplaces.

Celebrated a number of events to recognise and celebrate the achievements of women and our diverse staff including International Women’s Day, International Day of People with Disability, NAIDOC week, IDAHOBIT and Cultural Diversity Week.

## How we developed this Gender Equality Action Plan

### Gender Equality data analysis

The Gender Equality Act 2020 requires DPC to collect and report data on gender equality in the workplace against seven key indicators, which represent the areas where workplace gender inequality persists and where progress towards gender equality must be demonstrated.

Gender composition of the workforce

Gender composition of the Board

Gender pay equity

Workplace sexual harassment

Leave and flexibility

Recruitment and promotion

Gendered work segregation

DPC’s 2021 workplace gender audit was based on annual workforce data as at 30 June 2021 and included relevant results from the 2021 People Matter Survey. The audit included gender-disaggregated data analysis mapped against the seven workplace gender equality indicators, and considered intersectionality where possible. A summary of the key findings and insights from DPC’s workplace gender audit is presented at Attachment A.

### Consultation with stakeholders

The Gender Equality Act 2020 requires defined entities to undertake meaningful consultation and engagement with their governing bodies, employees, employee representatives and other relevant people to inform the development of their Gender Equality Action Plan.

- DPC’s first round of consultation involved briefing the DPC Board of Management, Executive teams, Group Senior Advisers and People & Culture on DPC’s key obligations under the Gender Equality Act 2020.

DPC also facilitated a series of workshops with People & Culture, the Gender Equality Working Group, DPC managers and staff, Staff Network representatives, and CPSU representatives and delegates to discuss the results of the workplace gender audit and identify strategies and actions for improving workplace gender equality across the department. The staff workshops were supplemented by an anonymous online survey to examine employee perceptions and experiences of gender equality in the workplace.

The second round of consultation focused on seeking feedback on the proposed strategies and actions from the DPC Board of Management, Gender Equality Working Group, the CPSU and key business units responsible for implementing the action plan to seek feedback.

The clear priorities that emerged from consultation included workforce diversity, gender pay equity, managing unconscious bias, flexible working practices, career development opportunities and eliminating negative workplace behaviours.

#### Stakeholder consultation

DPC Board of Management

DPC Executives

DPC People & Culture

DPC Gender Equality Working Group

DPC Managers and Staff (including Staff Network representatives)

CPSU Representatives and Delegates

### Intersectionality

DPC mapped and analysed each workplace gender equality indicator, where possible, by Aboriginality, age, disability, cultural background, religion, and sexual orientation. DPC also engaged with members of key staff networks to participate in the consultation process including the DPC Enablers Network, the Aboriginal Staff Network, the LGBTIQ+ Network and the VPS5 Network.

The Plan seeks to improve workforce diversity across all levels of the workforce, establish inclusive recruitment practices, create a safe, respectful, and inclusive workplace, and improve our data collection to better understand and address intersectional gender inequality in the workplace.

## Key actions

DPC identified six key actions areas for improving gender equality under the Plan based on the key findings of the workplace gender audit and the stakeholder consultation process.

The development of the Plan also considered a review of suggested strategies by the Commission for Gender Equality in the Public Sector and examples of good practice gender equality action plans previously developed by defined entities.

### Action areas

The Plan outlines the key goals and strategies that underpin each of the six key action areas. DPC will align the Plan with other diversity and inclusion plans as part the implementation plan and apply an intersectional lens to each workplace gender equality indicator where possible.

Accountabilities and timelines are assigned to each strategy including the relevant business owner(s) responsible for developing and implementing specific strategies. The key workplace gender equality indicators are also mapped against each strategy.

#### Gender Equality Action Plan 2021–2025

- Visible leadership and accountability – Senior leaders demonstrate commitment to gender equality and visibly champion and drive gender equality strategies.

Reducing the gender pay gap – DPC proactively seeks to better understand the factors that cause the gender pay gap and develops strategies, actions, policies, and processes to achieve gender pay equity.

Attracting, developing, and retaining a diverse, gender balanced and talented workforce – DPC is committed to recruiting and retaining a diverse, gender balanced and talented workforce and supporting the career advancement of women in the VPS.

Creating a safe, respectful, and inclusive workplace – DPC is committed to creating a safe, respectful, and inclusive workplace that takes a zero-tolerance approach to sexual harassment, violence, bullying and discrimination and supports people experiencing family violence.

Facilitating and promoting a flexible workplace – DPC is committed to facilitating and promoting a flexible workplace that encourages new ways of working and supports employees to balance work, family, and caring responsibilities.

Measuring, monitoring, and reporting on gender equality – DPC demonstrates its commitment to making reasonable and material progress towards achieving workplace gender equality by regularly measuring, monitoring, and reporting on workplace gender equality.

### Action Area 1: Visible leadership and accountability

Senior leaders demonstrate commitment to gender equality and visibly champion and drive gender equality strategies and initiatives

| Goal | Strategies | Workplace Gender Equality Indicator | Timing | Responsibility |
| --- | --- | --- | --- | --- |
| Ensure senior leaders visibly demonstrate commitment to achieving workplace gender equality | Establish the role of an Executive Champion for Gender Equality who takes responsibility for championing and driving gender equality strategies and initiatives at DPC. | All workplace gender equality indicators | Year 1 | DPC Board of Management |
|  | Establish a Diversity and Inclusion Committee comprising representatives from each Group to drive the implementation of the Gender Equality Action Plan (and Diversity and Inclusion action plans) and to ensure an intersectional approach. | All workplace gender equality indicators | Year 1 | People & Culture (Diversity & Inclusion) |
|  | At least twice per year, communicate DPC’s commitment to gender equality and progress towards achieving workplace gender equality including key issues, challenges, and achievements. | All workplace gender equality indicators | Ongoing (Year 1, 2, 3, 4) | Strategic Communications, Engagement and Protocol (Internal Communications) |
| Build senior leadership and manager capability to drive cultural change to achieve workplace gender equality | Develop and implement gender equality professional development for Executives and Managers focussing on workplace equality and respect, the effects of intersectionality (or compounding disadvantage), and unconscious bias. | All workplace gender equality indicators | Year 2 | People & Culture (Diversity & Inclusion) |
|  | Develop a Gender Equality toolkit and resources for Managers that contain a range of strategies on integrating gender equality into workplace policy, processes, and procedures across the employee life cycle. | All workplace gender equality indicators | Year 3 | People & Culture (Diversity & Inclusion) |
| Ensure the composition of the Board and Executive roles is diverse and gender balanced | Strive for a target of 50 per cent of women at the Board, maintain a target of 50 per cent of women at Executive levels, and strive for a diverse and proportional gender balance within Executive bands and at each level of leadership (monitor as part of the annual workplace gender audit). | Indicators 1&2: Gender composition at all levels of the workforce and governing bodies | Annual (Year 1, 2, 3, 4) | People & Culture (Diversity & Inclusion) DPC Executives |
|  | Review Executive recruitment policies and processes and consider actions to attract a more diverse range of applicants to senior leadership roles. | Indicators 1&2: Gender composition at all levels of the workforce and governing bodies | Year 2 | People & Culture (Recruitment & Workforce Services) |
| Promote and celebrate gender equality and intersectional diversity in the workplace | Develop and promote a program of activities and events championed by the Executive Champion for Gender Equality to raise awareness of gender equality and to showcase the experiences and achievements of women from a diverse range of backgrounds. | All workplace gender equality indicators | Ongoing (Year 1, 2, 3, 4) | Executive Champion for Gender Equality Strategic Communications, Engagement and Protocol (Internal Communications) |

### Action Area 2: Reducing the gender pay gap

DPC proactively seeks to better understand the factors that cause the gender pay gap and develops strategies, actions, policies, and processes to achieve gender pay equity

| Goal | Strategies | Workplace Gender Equality Indicator | Timing | Responsibility |
| --- | --- | --- | --- | --- |
| Develop strategies and actions to better understand and address the gender pay gap | Conduct an annual gender pay equity audit and develop and implement strategies and actions to reduce the gender pay gap (as part of the annual workplace gender audit). | Indicator 3: Gender pay equity | Annual (Year 1, 2, 3, 4) | People & Culture (Diversity & Inclusion) |
|  | Engage with women at DPC to examine views on the structural and individual factors that impact gender pay equity and identify actions for reviewing gender bias and discrimination in renumeration decisions. | Indicator 3: Gender pay equity | Year 2, 3 | People & Culture (Diversity & Inclusion) |
| Ensure fair and transparent Executive and VPS renumeration policies and processes | Develop a set of gender pay equity principles and guidelines to support Executive contract negotiations and remuneration review. | Indicator 3: Gender pay equity | Year 1 | People & Culture (Recruitment & Workforce Services/ Diversity & Inclusion) |
|  | Provide information and support to hiring managers and people managers to apply gender pay equity principles when considering VPS salary negotiations and offers. | Indicator 3: Gender pay equity | Year 2 | People & Culture (Recruitment & Workforce Services) |

### Action Area 3: Attracting, developing, and retaining a gender balanced and talented workforce

DPC is committed to recruiting and retaining a gender balanced and talented workforce and supporting the career advancement of women in the VPS

| Goal | Strategies | Workplace Gender Equality Indicator | Timing | Responsibility |
| --- | --- | --- | --- | --- |
| Reduce barriers to recruiting a gender balanced and diverse workforce | Review end-to-end recruitment and selection policies and processes and develop actions to ensure hiring practices are inclusive to all staff and free from unconscious bias. | Indicator 5: Recruitment and promotion | Year 2, 3 | People & Culture (Recruitment & Workforce Services) |
|  | Implement unconscious bias training for hiring managers and those on interview panels to help mangers better understand and eliminate bias from recruitment and selection processes. | Indicator 5: Recruitment and promotion | Year 2 | People & Culture (Diversity & Inclusion) |
| Support women’s career transition and progression from mid-senior VPS roles | Monitor career development and promotion data to understand if gender and / or diversity bias exists and consider actions to redress imbalance (as part of the annual workplace gender audit). | Indicator 5: Recruitment and promotion | Annual (Year 1, 2, 3, 4) | People & Culture (Diversity & Inclusion) |
|  | Identify and implement mentoring, career progression and leadership development opportunities to support women’s career transition and progression from mid-senior VPS roles. | Indicator 5: Recruitment and promotion | Year 2, 3 | People & Culture (Learning & Development) |
|  | Ongoing commitment to encourage more women into leadership roles through the continued delivery of external leadership and development programs. | Indicator 5: Recruitment and promotion | Annual (Year 1, 2, 3, 4) | People & Culture (Learning & Development) |
| Develop strategies to reduce workplace gendered segregation | Identify groups and occupations where there is an under or overrepresentation of women or men and consider strategies to redress this imbalance (as part of the annual workplace gender audit). | Indicator 7: Gendered work segregation | Annual (Year 1, 2, 3, 4) | People & Culture (Diversity & Inclusion) |
|  | Raise awareness of workplace gendered segregation and the impact gender stereotypes can have on women in the workplace. | Indicator 7: Gendered work segregation | Year 2 | Strategic Communications, Engagement and Protocol (Internal Communications) |

### Action Area 4: Creating a safe, respectful, and inclusive workplace

DPC is committed to creating a safe, respectful, and inclusive workplace that takes a zero-tolerance approach to sexual harassment, violence, bullying and discrimination and supports people experiencing family violence

| Goal | Strategies | Workplace Gender Equality Indicator | Timing | Responsibility |
| --- | --- | --- | --- | --- |
| Ensure employees experiencing or impacted by family violence feel safe and supported at work | Review DPC’s Family Violence policies, processes and supports to ensure they are victim-centric and reflect sector best practice. | Indicator 6: Flexible working and leave | Year 2 | People & Culture (Diversity & Inclusion / Health Safety & Wellbeing) |
|  | Continue to communicate that family violence is a workplace issue through raising awareness and promoting family violence policies, resources and supports available to employees experiencing family violence. | Indicator 6: Flexible working and leave | Ongoing (Year 1, 2, 3, 4) | Strategic Communications, Engagement and Protocol (Internal Communications) |
|  | Explore options to review and refresh family violence training for all Executives, managers, and Family Violence Contact Officers to assist them to support employees experiencing or impacted by family violence. | Indicator 6: Flexible working and leave | Year 2, 3 | People & Culture (Diversity & Inclusion / Health Safety & Wellbeing) |
| Ensure consistent promotion of a zero-tolerance approach to sexual harassment, violence, bullying and discrimination | Continued promotion of a zero-tolerance approach to sexual harassment, bullying, violence and discrimination via ongoing reporting of People Matter Survey results to the DPC Board of Management and consistent and ongoing messaging from the Secretary and Board of Management. | Indicator 3: Sexual Harassment | Ongoing (Year 1, 2, 3, 4) | Strategic Communications, Engagement and Protocol (Internal Communications) DPC Board of Management |
|  | Senior leaders and managers personally role model appropriate and respectful workplace behaviour and take a lead in respectfully challenging and responding to negative behaviours (as measured via People Matter Survey results). | Indicator 3: Sexual Harassment | Ongoing (Year 1, 2, 3, 4) | DPC Executives & Managers |
| Build employee confidence and capability to raise grievances and appropriately challenge and respond to negative behaviours. | Build employee confidence to report sexual harassment, violence, bullying and discrimination through ongoing review and evaluation of DPC’s inappropriate workplace behaviour policies, processes and reporting mechanisms (as measured via People Matter Survey results). | Indicator 3: Sexual Harassment | Year 2, 3 | People & Culture (Diversity & Inclusion / Health Safety & Wellbeing) |
|  | Regular DPC training for all staff and contractors around gender equality and appropriate and respectful behaviours in the workplace including sexual harassment, violence, bullying and discrimination. | Indicator 7: Gendered work segregation | Ongoing (every 2 years) | People & Culture (Health Safety & Wellbeing) |

### Action Area 5: Facilitating and promoting a flexible workplace

DPC is committed to facilitating and promoting a flexible workplace that encourages new ways of working and supports employees to balance work, family, and caring responsibilities

| Goal | Strategies | Workplace Gender Equality Indicator | Timing | Responsibility |
| --- | --- | --- | --- | --- |
| Demonstrate commitment to creating and maintaining a flexible workplace | Ensure senior leaders and people managers visibly role model flexible / hybrid working (including when staff return to workplaces in line with public-health advice). | Indicator 6: Flexible working and leave | Ongoing (Year 1, 2, 3, 4) | DPC Executives, Managers |
|  | Roll out DPCs flexible working policy and procedure (including an updated form to capture formal flexible working arrangements) with consideration to embedding an appropriate degree of flexibility into all roles. | Indicator 6: Flexible working and leave | Year 1 | People & Culture (Organisational Development) |
|  | Continued provision of education and resources to support Executives and Managers to effectively support the transition from remote working to a flexible/hybrid working model. | Indicator 6: Flexible working and leave | Year 2, 3 | People & Culture (Organisational Development) |
| Monitor and increase uptake of flexible working and leave arrangements | Monitor the uptake of flexible working and leave arrangements by gender and consider actions to increase uptake where required (as part of the annual workplace gender audit). | Indicator 6: Flexible working and leave | Annual (Year 2, 3, 4) | People & Culture (Diversity & Inclusion) |
| Support employees to balance work, family, and caring responsibilities | Support staff to manage work, family, and caring responsibilities through the ongoing provision of appropriate work/life balance information, resources, and programs. | Indicator 6: Flexible working and leave | Ongoing (Year 1, 2, 3, 4) | People & Culture (Organisational Development) |
|  | Identify actions to support women’s equal access to career progression and development opportunities while on any form of extended leave (e.g. parental, carers, cultural) to help minimise disruptions to advancing their career. | Indicator 5: Recruitment and promotion | Year 2, 3 | People & Culture (Organisational Development) |

### Action Area 6: Measuring, monitoring, and reporting on gender equality

DPC demonstrates its commitment to making reasonable and material progress towards achieving workplace gender equality by regularly measuring, monitoring, and reporting on workplace gender equality

| Goal | Strategies | Workplace Gender Equality Indicator | Timing | Responsibility |
| --- | --- | --- | --- | --- |
| Improve workforce data collection systems and processes | Review the workplace gender equality indicators and, where gaps exist, identify actions to establish a more robust dataset to support workplace gender audits (with a particular focus on intersectionality). | All workplace gender equality indicators | Ongoing (Year 1, 2, 3, 4) | People & Culture (Diversity & Inclusion) |
|  | Develop a campaign to encourage staff to complete personal/demographic information on relevant forms and surveys to improve DPC’s understanding of workplace diversity including issues and challenges. | Indicator 1: Gender composition at all levels of the workforce | Year 2, 3 | Strategic Communications, Engagement and Protocol (Internal Communications) People & Culture (Diversity & Inclusion) |
| Measure, monitor and report on progress against the Gender Equality Action Plan | Undertake a targeted annual workplace gender audit and develop a performance dashboard to support groups to develop strategies and actions to address gender equality and workplace diversity and inclusion gaps. | All workplace gender equality indicators | Annual (Year 1, 2, 3, 4) | People & Culture (Recruitment & Workforce Services/Diversity & Inclusion) |
|  | Prepare an annual report to the DPC Board of Management outlining progress against the Gender Equality Action Plan including key achievements, areas for improvement and proposed strategies to address areas of gender and intersectional inequality. | All workplace gender equality indicators | Annual (Year 2, 3, 4) | People & Culture (Diversity & Inclusion) |

## Leadership and resourcing

### Leadership and governance

DPC is committed to developing and implementing a Gender Equality Action Plan that is underpinned by strong leadership, governance, accountability, and reporting. DPC has established the role of an Executive Champion for Gender Equality at the Deputy Secretary level who is responsible for championing gender equality strategies and initiatives at DPC. The Executive Champion for Gender Equality will play an instrumental role in working with the DPC Board of Management to facilitate an enabling environment to advance gender equality at DPC.

A cross-functional Diversity and Inclusion Committee will be established to drive the implementation of the plan, comprising the business units responsible for implementing key strategies and actions under the plan and representatives from each Group who can progress and promote gender equality initiatives and report on progress at the Group level.

The Diversity and Inclusion Committee will also act as a formal consultation framework by ensuring gender equality advocates of all ages, gender identities, cultural backgrounds, sexual orientation, people with a disability, Aboriginal and Torres Strait Islander staff and male allies, are represented to ensure an intersectional approach to consultation when developing and implementing gender equality strategies and actions. It is intended that representatives of the Gender Equality, Enablers, Aboriginal, and LGBTIQ+ staff networks will sit on this group.

### Governance and resourcing

The implementation of the Plan will be coordinated by the Senior Adviser Diversity & Inclusion, within People & Culture. The Manager, Organisational Development will provide day-to-day direction for gender equality strategies. The Chief People & Transformation Officer will provide oversight of gender equality strategies.

Responsible business owner(s) have been assigned to lead the development and implementation of key strategies and actions under the plan that are relevant to their respective functions and operation. The budget for funding key strategies and actions in the plan including training and resources will be sourced from the central corporate development budget.

The table below provides an indicative summary of the annual commitment, resources and time that will be required to implement the gender equality action plan over the next four years.

#### Governance and strategic resource plan

| Function | Accountability | Resource/Time |
| --- | --- | --- |
| Governance | Board of Management | Annual meetings |
|  | Executive Champion for Gender Equality | Bi-annual meetings |
| Coordination | Senior Adviser Diversity & Inclusion | 0.5 FTE |
|  | Diversity and Inclusion Committee | Quarterly meetings |
| Capability Building | People & Culture | 0.2 FTE |
| Policy Review | People & Culture | 0.2 FTE |
| Data Analysis & Reporting | People & Culture | 0.2 FTE |
| Communication & Events | Strategic Communications | 0.1 FTE |

## Measuring progress and reporting

### Measuring progress

DPC will undertake an annual workplace gender audit to help track progress against key actions and measures in the Plan. This will help to monitor key metrics against the seven workplace gender equality indicators.

DPC will also develop a performance dashboard to help monitor and measure progress against the Plan (and other diversity and inclusion plans). All Groups will be encouraged to use the dashboard to identify gender equality initiatives to include in their group’s strategic plan and monitor and report progress.

### Reporting

Progress against the plan, including key achievements, areas for improvement and proposed strategies to address persistent issues, will be reported on annually to the Board of Management via the Executive Champion for Gender Equality. The Diversity and Inclusion Committee will also monitor progress against the implementation of the action plan via quarterly progress meetings.

As required under the Act, DPC will also report progress in relation to the strategies and actions set out in our plan to the Commission for Gender Equality in the Public Sector every two years. The reporting process will also include regular communication of progress against the Plan to DPC groups, employees, and employee representatives.

### Implementation

All strategies and actions will be set out in an implementation plan, a detailed internal monitoring and tracking document that will assist with monitoring and progress reporting. The implementation plan will outline the key timeframes for communicating, implementing, and reporting progress. The implementation plan will also outline the key measures that will help to report progress and outcomes against each workplace gender equality indicator.

## Attachment A: Analysing Gender Equality at DPC

The Gender Equality Act 2020 requires DPC to collect and report data on gender equality in the workplace against seven key indicators, which represent the areas where workplace gender inequality persists and where progress towards gender equality must be demonstrated.

- Gender composition of the workforce

Gender composition of the Board

Gender pay equity

Workplace sexual harassment

Leave and flexibility

Recruitment and promotion

Gendered work segregation

### Key findings and insights

DPC’s 2021 workplace gender audit was based on annual workforce data as at 30 June 2021 and includes relevant results from the 2021 People Matter Survey. The audit included gender-disaggregated data analysis mapped against the seven workplace gender equality indicators, and considered intersectionality where possible. A summary of the key findings and insights from DPC’s workplace gender audit is presented below.

#### Indicator 1: Gender composition of the workforce

Women are over-represented at DPC with 60.6 per cent of staff identifying as women, 39.2 per cent as men and 0.2 per cent as self-described.

A higher proportion of men (93 per cent) work full time compared to women (81 per cent), while a higher proportion of women (18 per cent) work part-time compared to men (6 per cent).

There appears to be a gendered difference in the proportion of survey respondents who agreed with the statement: ‘There is a positive culture within my organisation in relation to employees of different sexes/genders’ – 90 per cent of men agreed with this statement, compared to 86 per cent of women and 74 per cent of staff who identify as non-binary (or prefer not to say).

#### Indicator 2: Gender composition of the governing body

There is a good representation of women on the DPC Board, with 43 per cent of board members identifying as female and 57 per cent as male.

#### Indicator 3: Gender pay equity

DPC’s annualised median2 base salary pay gap stands at 1.8 per cent, which means women on average earn $1,983 per year less than men.

DPC’s median total renumeration pay gap stands at -0.2 per cent, meaning women on average earn $194 per year more than men.

#### Indicator 4: Workplace sexual harassment

The 2021 People Matter Survey identified that 2 per cent of men, 2 per cent of women and 1 per cent of people who identify as non-binary (or prefer not to say) experienced sexual harassment in the workplace.3

#### Workplace sexual harassment

|  | Male | Female | Non-binary/prefer not to say |
| --- | --- | --- | --- |
| % Agree | 89% | 85% | 72% |
| “My organisation encourages respectful workplace behaviours.” | 92% | 90% | 72% |
| “My organisation takes steps to eliminate bullying, harassment and discrimination.” | 82% | 76% | 62% |
| “I feel safe to challenge inappropriate behaviour at work.” | 86% | 75% | 49% |

- Women and staff who identify as non-binary (or prefer not to say) were less favourable to the following statements:

‘My organisation encourages respectful workplace behaviours’

‘My organisation takes steps to eliminate bullying, harassment and discrimination’

‘I feel safe to challenge inappropriate behaviour at work.’

#### Indicator 5: Recruitment and promotion

Women and staff who identify as non-binary (or prefer not to say) were less favourable to the following statements:

‘My organisation makes fair recruitment and promotion decisions, based on merit’ – 62 per cent of women and 45 per cent of staff who identify as non-binary (or prefer not to say) agreed with this statement compared to 72 per cent of men.

‘I feel I have an equal chance at promotion in my organisation’ – 45 per cent of women and 23 per cent of staff who identify as non-binary (or prefer not to say) agreed with this statement compared to 58 per cent of men.

There appears to be a gendered difference in how people responded to the statement: ‘Gender, Aboriginality, cultural background, sexual orientation, disability and age is not a barrier to success in my organisation’ – a higher proportion of women and staff who identify as non-binary (or prefer not to say) were largely less favourable than men that these factors were not a barrier to success in their organisation.

#### [Factor] is not a barrier to success in my organisation

| % Agree | Male | Female | Non-binary/prefer not to say |
| --- | --- | --- | --- |
| Age | 69% | 65% | 53% |
| Gender | 83% | 82% | 65% |
| Sexual orientation | 81% | 82% | 71% |
| Cultural background | 73% | 69% | 59% |
| Aboriginality | 66% | 64% | 51% |
| Disability | 65% | 55% | 56% |

#### Indicator 6: Leave and flexibility

The main types of formal flexible working arrangements accessed by staff at DPC include flexible start and finish times, working part time and working more hours over fewer days. A higher proportion of women and staff who identify as non-binary (or prefer not to say) reported using these flexible working arrangements compared to men.4

A higher proportion of men (38 per cent) and staff who identify as non-binary (or prefer not to say) (34 per cent), reported using no flexible working arrangements compared to women (29 per cent).

#### Flexible working arrangement

|  | Working more hours over fewer days | Flexible start and finish times | Working part-time | Don’t use any flexible work arrangement |
| --- | --- | --- | --- | --- |
| - Men | - 5% | - 31% | - 4% | - 38% |
| - Women | - 8% | - 39% | - 14% | - 29% |
| - Non-binary/prefer not to say | - 8% | - 33% | - 9% | - 34% |

A higher proportion of women (78 per cent) than men (22 per cent) took parental leave during the reporting period.5

There appears to be a gendered difference in how people feel about flexible working arrangements, family and caring responsibilities, and support for taking family violence leave at DPC.

A higher proportion of women (87 per cent) agreed with the statement: ‘My organisation would support me if I needed to take family violence leave’ compared to men (84 per cent) and staff who identify as non-binary (or prefer not to say) (76 per cent).

Staff who identify as non-binary (or prefer not to say) (84 per cent) were less favourable than men or women (90 per cent) with regards to the statement ‘I am confident that if I requested a flexible work arrangement, it would be given due consideration.’

Staff who identify as non-binary (or prefer not to say) (77 per cent) were less favourable than men (89 per cent) and women (90 per cent) with regards to the statement ‘My organisation supports employees with family or other caring responsibilities, regardless of gender.’

#### Indicator 7: Gendered work segregation

The gender composition of ANZSCO code6 major groups7 indicates that a higher proportion of men (24 per cent) occupy Management roles than women (21 per cent).

A relatively equal proportion of men (50 per cent) and women (49 per cent) occupy Professional roles; however men dominate ICT professions (19 per cent men, compared to 10 per cent women) and women are over-represented in Business, HR and Marketing roles (74 per cent women, compared to 64 per cent men).

A higher proportion of women are employed in Clerical and Administrative roles (29 per cent) compared to men (18 per cent).

There is an overrepresentation of men (8 per cent) who work as Machinery Operators and Drivers compared to women (1 per cent).

| ANZCO Major Group | Men | Women | Total |
| --- | --- | --- | --- |
| Managers | 24% | 21% | 22% |
| Professionals | 50% | 49% | 49% |
| Technicians and Trades Workers | 1% | 0.2% | 1% |
| Clerical and Administrative Workers | 18% | 29% | 24% |
| Machinery Operators and Drivers | 8% | 1% | 4% |
| Total | 100% | 100% | 100% |

1	Commission for Gender Equality in the Public Sector.

2	The median is considered to be a more accurate measure of the gender pay as it is not skewed by the lowest and highest rates of pay or ‘outliers’.

3	DPC is unable to provide the number of formal sexual harassment complaints made (<10) to protect privacy and confidentiality of complainants.

4	DPC does not currently collect workforce data on formal flexible working arrangements. The different types of formal flexible working arrangements utilised by staff are captured in the People Matter survey.

5	DPC is unable to provide the number of people who exited the organisation during parental leave (<10) to protect privacy and confidentiality of staff who took parental leave.

6	ANZSCO is the skill-based classification used to categorise all occupations and jobs undertaken for profit in the Australian and New Zealand labour markets.

7	DPC employs very few or no Technicians and trades workers, Community and personal service workers, Sales workers, and Labourers.