## V Form D-QTR
| V Form D-QTR | QUARTERLY ESSENTIAL PUBLIC ASSET RECONSTRUCTION WORKS REPORT
Delivery Agency: <name of Delivery Agency>
Quarterly Report completed by: <name of Delivery Agency Officer who has completed this report> | [28 empty] | Assessing Authority Assessor: <name of Assessor who has reviewed this report>
Date Quarterly Report completed : <Date Quarterly Report completed i.e. 12 July 2022> | [28 empty] | Date Quarterly Report reviewed : <Date Quarterly Report reviewed i.e. 12 July 2022>
[5 empty] | Timing |  |  |  |  | All of Project ($m) |  |  |  |  | Project To Date ($m) |  |  | Yearly Budget ($m) |  |  |  |  | Yearly Actuals ($m) | [5 empty] | Commentary
Delivery Agency: <name of Delivery Agency> | Claim ID (Asset ID #) | Project Life Cycle: (select from: Planning Stage; Tender Stage; Construction Stage & Practical Completion) | Procurement approach (select from Open, Selective and Limited - if Limited tender undertaken, please specify reason in comments section) | Risk Status (Green - low risk assets to be reconstructed i.e. sealed roads, Amber - some complicated assets to be reconstructed within certified estimates package, Red - high risk assets i.e. landslips) | Timing Delivery Status (Green - on schedule, Amber - Some risks are emerging that are affecting or likely to affect significant milestones, project scope or contract variations, Red - Behind schedule) | Month/Year Certified Estimate Approval Date | Required Completion Date | Forecast Completion Date | Revised Forecast Completion Date | Budget Delivery Status (Green - budget on line with certified estimate, Amber - some risks are emerging that are affecting or likely to affect budget delivery i.e. project scope or contract variations, Red - exceeding certified estimate) | Approved Certified Estimate | Project contingency within Approved Certified Estimate | Current Year Approved Budget | Expend to Last FY | PTD Budget | PTD Actual | PTD Variance | Q1 | Q2 | Q3 | Q4 | YTD Total | Q1 | Q2 | Q3 | Q4 | YTD Total | YTD Variance | Overview Delivery Agency Comment. To include comments on: > risks on meeting project timeline and budget; > where no open tender process has been undertaken specify reason: > use of project contingency | Assessing Authority Comments on progress and any resulting issues
Delivery Agency Projects
Total number of projects is : 1 | [9 empty] | Totals for Delivery Agency Projects : | 11000000 |  | 8000000 | 0 | 0 | 500000 | 500000 | 0 | 1000000 | 2000000 | 5000000 | 8000000 | 0 | 500000 | 0 | 0 | 500000 | -7500000 | COMMENTS | COMMENTS
Example 1 - Council XX, Package Works 1, AGRN XXX (ME- 900125) |  | Construction Phase | Open Tender | Low | Green | 2019-07-17 | 2021-06-01 | 2020-12-01 | 2020-12-01 | Green | 11000000 | 1000000 | 8000000 | 0 | 0 | 500000 | 500000 | 0 | 1000000 | 2000000 | 5000000 | 8000000 | 0 | 500000 | 0 | 0 | 500000 | -7500000

## Assumptions_GEN (hidden)
Asset category
Transport Infrastructure
Public Infrastructure
Asset Sub-Category
Roads
Road Infrastructure
Pedestrian Bridges
Footpaths and Bike Lanes
Bridges
Tunnels
Culverts
Public Hospitals
Public Schools
Public Housing
Prisons/ Correctional Facilities
Police, Fire and Emergency Services' Stations
Levees
State/ Territory or Local Government Offices
Stormwater Infrastructure
Asset Type
Unsealed Pavements
Sealed Pavements
Road Furniture and Delineation
Concrete
Drainage Structure
Other
Treatment ID
ST1
ST2
ST3
ST4
ST5
ST6
ST7
ST8
ST9
ST10
ST11
ST12
ST13
ST14
ST15
ST16
ST17
ST18
ST19
ST20
ST21
ST22
ST23
ST24
OT1
Treatment Type
EW List | EW |  | IR/RW | IR/RW list
ST1 Light formation grading |  |  |  | ST1 Light formation grading
ST2 Medium formation grading |  |  |  | ST2 Medium formation grading
ST3 Heavy formation grading |  |  |  | ST3 Heavy formation grading
ST4 Gravel material supply |  |  |  | ST4 Gravel material supply
ST9 Patch repair – patch unbound pavement failure |  |  |  | ST5 Gravel resheeting
ST10 Pothole repair |  |  |  | ST6 In-situ stabilisation – including additional material as required
ST11 Heavy shoulder grading |  |  |  | ST7 Granular overlay – overlay with imported material (≤150mm)
ST14 Bulk excavate surplus material or debris and remove from site |  |  |  | ST8 Reconstruct unbound granular pavement
ST15 Bulk fill |  | Patch repair – patch unbound pavement failure |  | ST9 Patch repair – patch unbound pavement failure
ST16 Rock protection |  | Pothole repair |  | ST10 Pothole repair
ST17 Reshape table drain |  | Heavy shoulder grading |  | ST11 Heavy shoulder grading
ST18 Replace road signage |  | Shoulder reconstruction |  | ST12 Shoulder reconstruction
ST19 Replace roadside barriers |  | Asphalt |  | ST13 Asphalt
ST20 Replace guide posts or markers |  | Bulk excavate surplus material or debris and remove from site |  | ST14 Bulk excavate surplus material or debris and remove from site
ST21 Reconstruct reinforced concrete |  | Bulk fill |  | ST15 Bulk fill
ST22 Repair drainage structure – excavate, repair and reinstate |  | Rock protection |  | ST16 Rock protection
ST23 Replace Reinforced Concrete Box Culvert (RCBC) |  | Reshape table drain |  | ST17 Reshape table drain
ST24 Replace concrete pipe |  | Replace road signage |  | ST18 Replace road signage
OT1 ‘Other’ – including structures, retaining items and removal of debris from essential public infrastructure |  | Replace roadside barriers |  | ST19 Replace roadside barriers
ST25 Clear disaster related silt & debris from guttering, drains, stormwater infrastructure impacting on public infrastructure (e.g. schools, hospitals not covered by insurance) |  | Replace guide posts or markers |  | ST20 Replace guide posts or markers
ST26 Clearing and removal of disaster related fallen or damaged trees & vegetation |  | Reconstruct reinforced concrete |  | ST21 Reconstruct reinforced concrete
ST27 Processing of stockpiled disaster related fallen or damaged trees, vegetation & green waste |  | Repair drainage structure – excavate, repair and reinstate |  | ST22 Repair drainage structure – excavate, repair and reinstate
ST28 Inspection costs associated with identifying Emergency Works |  | Replace Reinforced Concrete Box Culvert (RCBC) |  | ST23 Replace Reinforced Concrete Box Culvert (RCBC)
ST29 Traffic management including temporary lights, closures, fencing, signs |  | Replace concrete pipe |  | ST24 Replace concrete pipe
|  | ‘Other’ – including structures, retaining items and removal of debris from essential public infrastructure |  | OT1 ‘Other’ – including structures, retaining items and removal of debris from essential public infrastructure
ST1 Light formation grading
ST2 Medium formation grading
ST3 Heavy formation grading
ST4 Gravel material supply
ST5 Gravel resheeting
ST6 In-situ stabilisation – including additional material as required
ST7 Granular overlay – overlay with imported material (≤150mm)
ST8 Reconstruct unbound granular pavement
ST9 Patch repair – patch unbound pavement failure
ST10 Pothole repair
ST11 Heavy shoulder grading
ST12 Shoulder reconstruction
ST13 Asphalt
ST14 Bulk excavate surplus material or debris and remove from site
ST15 Bulk fill
ST16 Rock protection
ST17 Reshape table drain
ST18 Replace road signage
ST19 Replace roadside barriers
ST20 Replace guide posts or markers
ST21 Reconstruct reinforced concrete
ST22 Repair drainage structure – excavate, repair and reinstate
ST23 Replace Reinforced Concrete Box Culvert (RCBC)
ST24 Replace concrete pipe
OT1 ‘Other’ – including structures, retaining items and removal of debris from essential public infrastructure
Claim Type
Emergency Works
Immediate Reconstruction Works
Reconstruction of Essential Public Assets
IR
RW
Relief and Recovery
Counter Disaster Operations
Yes/No
Yes
No
End of worksheet
Green | On Schedule
Amber | Risks are emerging that could affect completion of works i.e. projects likely to miss signficant milestones or have project scope or contract variations
Red | Behind Schedule