Date: (for the purposes of version control)

Essential Public Asset Reconstruction Estimates Validation Checklist

| AGRN #: |  |
| --- | --- |
| Event: |  |
| CMS Reconstruction Works Estimate Package No. Reference #: |  |
| CMS Claim No. Reference #: |  |
| Delivery Agency: |  |
| Delivery Agency certified estimate ($): |  |
| Delivery Agency certification date: |  |
| Assessing Authority recommendation ($): |  |
| Assessing Authority recommendation date: |  |
| Date works are to be completed: |  |
| Date that claims can be submitted: | Up to 31 July of each year relating to expenditure incurred in the previous financial year. |

| Damage Assessment and Cost Estimation |  |
| --- | --- |
| Step | Activity |
| 1 | Under the DRFA, the Australian Government will reimburse the states under an estimates-based model for the Reconstruction of Essential Public Assets (REPA) following an eligible disaster. The DRFA specifies that: “States must establish the estimated reconstruction cost for the reconstruction of an essential public asset through: - market response, or - cost estimation. A critical step in this process is the estimate of the reconstruction cost of the essential public asset and identification of a total project cost. States must develop the estimated reconstruction cost for the reconstruction of an essential public asset comprising eligible state expenditure for construction, design and project management, contingency and cost escalation.” (DRFA 2018, Section 6.4.2–6.4.3 |
| 2 | Damage Assessment Identification of damage, scoping of works, investigations and design and estimation of project costs should occur as soon as reasonably practical following an event. Note that the Commonwealth auditors have raised the lack of damage in photographs in 2019 following an audit of natural disaster expenditure. Where damage is not evident, Assessors could undertake site inspections and detail this sufficiently across particular assets in their notes to ensure that damage has occurred following a disaster rather than general wear and tear. Endeavours should be made to sufficiently design, quantify and mitigate project specific risks to provide greater confidence in the estimated project costs. Estimates must be submitted to the Assessing Authority no later than 31 March in the financial year after the eligible disaster occurred, and prior to undertaking the reconstruction works. REPA works must be completed within two (2) years from the end of the financial year in which the eligible disaster occurred. |
| 3 | Primary Asset Function The Delivery Agency must identify and record primary asset function and classification that complies with the DRFA’s Essential Public Asset Function Framework. |
| 4 | Projects Cost Estimates are to be based on projects. A “project” shall be considered one of the following: - a single essential public asset, or - a group of related essential public assets which could be contracted jointly. For the purposes of ongoing document control and audit, efforts should be made to align submissions with the intended packaging of works for delivery or contract. All reconstruction projects within a given financial year should be included in a single claim to the Assessing Authority. |
| 5 | Estimated reconstruction costs calculation The estimated reconstruction cost should be established by determining the base estimate on which contingency and escalation is applied as a percentage. The base estimate should include: - direct costs - indirect costs (design and project management costs). Estimates must be done by project. For the purpose of defining a project, a project shall be considered one of the following: - a single essential public asset, or - a group of related essential public assets which could be contracted jointly. For the purposes of ongoing document control and audit, efforts should be made to align submissions with the intended packaging of works for delivery or contract. For further detail on direct and indirect costs please refer to Guideline 2 – Cost Estimation. |

DRFA Cost Estimation Validation Checklist

| Check No. | Checks to be undertaken | Assessing Authority Checks | Administering Authority Checks |
| --- | --- | --- | --- |
| 1 | Does the Estimates Package relate to an eligible DRFA or NDFA event? (DRFA Objective N1.1, DRFA Clause No. 5.1). | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 2 | Have all fields on form V Form-D-DEC been completed correctly? (DRFA Objective C3, DRFA Clause 6.4.7) - Event ID relating to the Australian Government Reference Number (AGRN) associated with the disaster - The Claim Type - The Eligible Event name - Name of the Delivery Agency - Does the amount in the DEC form match the V Form -C-RW? - Has the Claim Lodgement Declaration Form (Form ID V Form D-DEC been signed by the Preparer and Chief Executive Officer of the Delivery Agency? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 3 | Have all fields in the V Form-C-RW form been completed correctly? (DRFA Objective D1, D2, C1, C2, DRFA Clause No. 5.1, 6.1, 6.2, 6.4.7) | Y ☐; N ☐; N/A ☐. Assessor to add commentary below where an item has not been met. | Y ☐; N ☐; N/A ☐. |
|  | - Are each of the assets listed an essential public asset? (DRFA Objective D2, DRFA Clause 6.1, 6.2) |  |  |
|  | - Has the Assessing Authority undertaken a sample review of the Delivery Agency’s Asset Register for some of the assets listed in the V Form-C-RW form including those assets that appear not to be essential public assets and also verified that the asset location aligns with that included by the Delivery Agency in the columns M to P in the V Form-C-RW form ? (DRFA Objective D1.2, DRFA Clause 6.1, 6.2) |  |  |
|  | - Does each asset listed in the V Form-C-RW form comply with the DRFA’s Essential Public Asset Function Framework (this cannot be verified if columns C to H are not filled in)? (DRFA Objective C1, C2, DRFA Clause 6.3, 6.4) |  |  |
|  | - Will the estimated reconstruction costs for the proposed reconstruction works restore the asset to the pre-disaster function and not include any increased resilience (betterment) of the asset? (DRFA Objective C1, C2, DRFA Clause 6.3, 6.4) |  |  |
|  | - Are the estimated reconstruction costs developed in accordance with the DFRA arrangements? (DRFA Objective C3, DRFA Clause 6.4.7) |  |  |
| 4 | Have the assets and proposed works been assessed with consideration to ineligible expenditure as per Guideline 1: Claims and eligibility for essential public assets (Category B) pages 31-33? Where an Eligibility Enquiry form has been submitted to NEMA, why was eligibility questioned, and what was the outcome of the enquiry? (DRFA Objective D2, DRFA Clause 6.1, 6.2) | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 5 | Have indirect costs such as those relating to project management (i.e. engineering, eligible positions approved by the Administering Authority) been included in the estimated reconstruction costs and within the percentage ranges identified in section 4.5 of Guideline 2 and as per the typical ranges identified in the second table of section 4.5? Do these indirect costs appear ‘reasonable’? Are the indirect costs fully transparent in either the cost estimation tool for a particular asset or the V Form-C-RW? (DRFA Objective C3, DRFA Clause 6.4.7) | Y ☐; N ☐; N/A ☐. PM; I&D; CA. | Y ☐; N ☐; N/A ☐. |
| 6 | Is this Works Estimates Package based on market response or on a ‘first principles’/benchmarking approach? (DRFA Objective C3, DRFA Clause 6.4.7) | Market Response ☐. First principles ☐. Other ☐. Assessor Commentary:. |  |
| 7 | Where a Delivery Agency has provided cost estimates based on market response, have they included a cost escalation amount in the RW form? (DRFA Objective C3, DRFA Clause 6.4.7) Escalation amounts are only eligible based on cost estimation using the ‘first principles’/benchmarking approach. Therefore, any cost escalation amounts for a market response estimate should be deemed ineligible. For estimates developed using the ‘first principles’/benchmarking approach, please provide commentary on whether the Delivery Agency has provided a cost escalation calculation tool (Form VT-CEsc) to determine the percentages to be used across the applicable financial years used are within the ranges outlined in section 4.4 of Guideline 2? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 8 | Are key estimated cost assumptions ‘reasonable’ for contingency and within the percentage ranges identified in section 5.4 of Guideline 2 for: - ‘First principles’/benchmarking estimate – table 1; or - Market response – table 2. For market response, a lower contingency should be considered as prior to seeking a market response, investigations should have been carried out and the design developed sufficiently to enable pricing by the market. Please provide commentary on what is included in contingency and whether the percentages used are within the ranges outlined in section 5.4 of Guideline 2? Reasonable is defined when the estimated reconstruction costs is comprehensive and addresses risks in a prudent manner. However, the principle of prudence should not be advanced as a reason to support deliberate and excessive caution that brings undesirable bias. (DRFA Objective C3, DRFA Clause 6.4.7) | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 9 | Delivery agencies are required to only utilise the C-RW form to apply contingency for estimates using the ‘first principles’/benchmarking approach. (DRFA Objective C3, DRFA Clause 6.4.7) Please provide commentary on whether amounts relating to contingency have been duplicated in both the C-RW form or the cost estimation tool (for ‘first principles/benchmarking approach) or the tender (for the market response approach). Note that no amounts should be included in the contingency calculator if already included in the tender (market response). | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 10 | For market response estimates, have provisional / additional works items been included as part of the contingency amount for the Works Estimates Package? If not, the RW form will need to be amended by the Delivery Agency to reflect this. (DRFA Objective C3, DRFA Clause 6.4.7) | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 11 | Post-disaster damage evidence (DRFA Objective D3.1, 3.2, D5.1, D5.2, DRFA Clause No. 6.1, 6.2). - Has evidence such as geospatial data (i.e. satellite images), visual data (including photos or video footage), or asset inspection reports conducted or verified by a suitably qualified professional been provided by the Delivery Agency? - Where photos have been provided, have the photos been referenced uniquely and included in the V Form-C-RW form? (Note references such as “Refer to CMS” is not appropriate. Where two or more asset types have been damaged on a particular asset i.e. road, if they are not located in the same vicinity, have further photos been provided and referenced appropriately? - Has the Delivery Agency provided photo files in addition to the photo reports which show the meta data intact and the time taken? - Are the photo files grouped by asset and referenced uniquely? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 12 | Photo report – Post disaster damage evidence (DRFA Objective D3.1, 3.2, D5.1, D5.2, DRFA Clause No. 6.1, 6.2) - Has the Delivery Agency provided photo reports as per the Photo Report Template – Essential Public Assets Reconstruction works Estimate (https://www.emv.vic.gov.au/drfa/guideline-1-photo-template) for each asset included on the C-RW form? - Does the Photo report include the following information: - Damaged locations (latitude and longitude)? - Date the photos were taken? - Are the Photos presented in a logical sequence for each asset with the asset name and reference number (where available)? - For damage that is continuous, the frequency of the photos should depict that the damage is continuous and not intermittent. - Do all damage photos demonstrate that damage has occurred? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 13 | Photo report – Sample review (DRFA Objective D3.1, 3.2, D5.1, D5.2, DRFA Clause No. 6.1, 6.2) - Has the Assessing Authority undertaken a sample review of the photo reports and provided commentary in this checklist and/or an attachment outlining the sampling approach including the: - sample size undertaken; - photos reviewed; - geospatial locations (i.e., latitude and longitude) provided in the photo reports against the meta data in the separate photo files (i.e., jpg photos), as well as any software or applications used by the Delivery Agency that captures the actual data, to ensure that works is associated with the correct asset; as well as the - outcome of the sampling? - Sampling needs to include a review of the geospatial locations (i.e., latitude and longitude) provided in the photo reports against the meta data in the separate photo files i.e., jpg as well as any software used by the Delivery Agency that captures this actual data, to ensure that works is associated with the correct asset. | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 14 | Pre-condition Assessment Report (DRFA Objective D5.1, D6, DRFA Clause No. 6.1, 6.2) - Has the Delivery Agency provided the information using the Pre-condition Assessment report which is signed by a suitably qualified professional (including identifying the document reference name), required to determine the pre-disaster asset function from either of the following: - Asset register - Certification reports - Inspection reports - Maintenance reports - Visual data – photos, videos etc - Does the supporting documentation regarding the pre-condition of the damaged asset no older than four years before the eligible disaster for each asset? - Have all reports been verified and signed off by the Assessing Authority Assessor? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 15 | Have the estimated reconstruction costs been verified by a suitably qualified officer within the Delivery Agency (a person with relevant tertiary qualification and a minimum of five years’ experience in the appropriate field of work for the asset type, or a person with the appropriate level of expertise and experience within the Delivery Agency at the Director level, for example, Director Infrastructure or its equivalent.)? Have you sighted their qualifications and placed a copy in the CMS? (DRFA Objective C2, C3, DRFA Clause No. 6.3, 6.4, 6.4.7) | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 16 | Are the estimated reconstruction costs accurately recorded and allocated to a project and each project linked to an AGRN? Does the amount per Asset ID. no in V Form C-RW reconcile with the amount in the Cost Estimation tool or the market response? (DRFA Objective C3, DRFA Clause 6.4.7) | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 17 | Has a schedule of rates been provided by the Delivery Agency and been placed into the CMS? For the market response approach, this should be provided as part of the tender documentation if it is based on a schedule of rates contract and the Assessor should confirm if this is reasonable. This does not apply to lump sum tenders. Where this relates to a ‘first principles’/benchmarking approach, this should be provided by the Delivery Agency. Have you sampled various estimated cost components against benchmark of costs (using other claims provided by this Delivery Agency or other Delivery Agencies) and material variances appropriately explained? Please provide commentary on the sampling approach undertaken. (DRFA Objective C3, DRFA Clause 6.4.7) | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 18 | Have all supporting documentation provided in the CMS by the Delivery Agency been structured as per the following: - Damage sub folder - Pre-condition sub folder - Pre-condition reports – signed - Pre-condition evidence (such as maintenance and inspection logs) - Estimate | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 19 | Other Notes from Assessor ## Input feedback if required General Feedback for Delivery Agency ## Input feedback if required |  |  |

Assessing Authority Officer Declaration:

I hereby declare that the claim has been assessed for completeness and accuracy.

Signed:

Date:

Administering Authority Officer Declaration:

I hereby declare that the claim has been assessed for completeness and accuracy.

Signed:

Date:

| Essential Public Asset Reconstruction Works Claims Validation Process |  |
| --- | --- |
| Step | Activity |
| 1 | An essential public asset directly damaged by an eligible disaster event, or a re-damaged essential public asset, may be reconstructed to its pre-disaster function. The selected reconstruction treatment must be consistent with the DRFA Essential Public Asset Function Framework (DRFA Clause 6.3). Essential public asset reconstruction works undertaken within playgrounds, parks, gardens, reserves, access tracks, fire trails and walking trails are considered ineligible. Cost estimates for reconstruction of essential public assets must be submitted to the Assessing and Administering Authorities concurrently within nine (9) months after the end of the financial year in which the eligible disaster event occurred. The State must approve and lodge to the Australian Government the estimated cost of reconstruction works within twelve (12) months after the end of the financial year in which the eligible disaster event occurred. Essential public asset reconstruction works are to be completed within two (2) years after the end of the financial year in which the eligible disaster event occurred. Where a claim or project is not lodged by the timeframes outlined above, these works may not be approved and cannot proceed under that eligible disaster event |
| 2 | Extension of Time Requests Where the Delivery Agency has demonstrated that the delays to finalising works are a result of exceptional circumstances that are either unforeseeable or beyond the control of the Delivery Agency, they can make an Extension of Time (EOT request). EOT requests are required to be lodged at least three (3) months prior to the end of the 24 (24) month time limit. Requests for extension of time received by the Assessing Authority after the allowable time limits have expired will not be considered. Delivery Agencies are required to complete DRFA EOT Request Form – Reconstruction Works. The Assessing Authority will consider EOT requests, and then provide recommendations to the Administering Authority which has the authority to approve the extension. The Assessing Authority is to assess and complete the EOT Request Form for the Administering Authority approval. The Administering Authority, following the Commonwealth’s approval, may approve an EOT. In the event that an EOT is not approved, any expenditure incurred beyond the required date will be ineligible. |
| 3 | Before essential public asset reconstruction works are to commence, approval must be sought from the Assessing Authority and the Administering Authority. As part of the essential public asset reconstruction works claim, the Delivery Agency must demonstrate that the reconstructed essential public asset will perform the same function as prior to the eligible disaster event. To support this process, Delivery Agencies are required to lodge either a cost estimate or open tender price for each essential public asset reconstruction works project by nine (9) months from the end of the financial year in which the eligible disaster event occurred. |
| 4 | Claims for essential public asset reconstruction works is to be lodged to the Assessing Authority in the financial year that the expenditure is incurred. Regular claims are encouraged. The Assessing Authority will consult with the Delivery Agency to ensure all available information has been appropriately considered as part of the claim. Once a claim has been assessed by the Assessing Authority and approved by the administrating authority a notification to the Delivery Agency will be issued. Payment will be issued, subject to the payments already received to date by the Delivery Agency for that claim. All acquitted claims may be subject to further review by the Australian Government for compliance, in accordance with the provisions outlined in the DRFA. For the claim, the following components are to be provided - Claims lodgement declaration form (Form ID VF-D-DEC) - Completed EPA reconstruction works claim template (Form ID V Form-C-RW) - Cost Estimate - General ledger or transaction listing - Payroll reports - Invoices - Pre-condition Assessment Report - Photo Report – Post Disaster Damage - Photo Report – Works undertaken - Photo Files |
| 5 | If the claim from the Delivery Agency is complete and accurate, the Assessing Authority will endorse/approve the claim. |
| 6 | If the claim from the Delivery Agency requires corrective action, the Assessing Authority will return the incomplete claim form to the Delivery Agency for further action. When the LGA returns completed claim form, the Assessing Authority will refer to Step 1 and 2. |

## DRFA Claim Validation Process Checklist – Essential Public Asset Reconstruction Works

| Check No. | Checks to be undertaken | Assessing Authority Checks | Administering Authority Checks |
| --- | --- | --- | --- |
| 20 | Have all fields on form VF-D-DEC been completed correctly? (DRFA Objective C3, DRFA Clause 6.4.7) | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
|  | - Event ID relating to the Australian Government Reference Number (AGRN) associated with the disaster |  |  |
|  | - The Claim Type |  |  |
|  | - The CMS Claim number and Eligible Event name |  |  |
|  | - Name of the Delivery Agency |  |  |
|  | - Does the amount in the DEC form match the lodged amount in the Claims Management System (CMS), the V Form -C-RW and general ledger/transaction report unless a reconciliation statement is provided (if the evidence of expenditure differs from the amount claimed)? |  |  |
|  | - Has the Claim Lodgement Declaration Form (Form ID V Form D-DEC been signed by the Preparer and Chief Executive Officer of the Delivery Agency? |  |  |
| 21 | Does each line on form VF-C2-CW represent an asset where works were undertaken: |  |  |
|  | - All fields on V Form C2-CW are filled in and completed correctly? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
|  | - Each asset is eligible as an essential public asset? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
|  | - Each asset complies with the DRFA’s Essential Public Asset Function Framework (this cannot be verified if columns C to F are not filled in)? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
|  | - Assets have been restored to the Pre-Disaster Function and usage, adopting relevant technical standards? (DRFA Objective C5, DRFA Clause 7.1.9) | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
|  | - Have photos been referenced uniquely and included in the form? (Note references such as “Refer to the CMS” are not appropriate. Where two or more asset types have been damaged on a particular asset i.e. road, if they are not located in the same vicinity, have further photos been provided and referenced appropriately? (DRFA Objective D4, DRFA Clause 6.1, 6.2) | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
|  | Assessor comments |  |  |
| 22 | Has the Delivery Agency has provided required evidence to support the claim (DRFA Objective C5, DRFA Clause No. 7.1.9) |  |  |
| 22a) | - General ledger/transaction listing - This must correlate to expenditure in V Form-C-RW - This must include minimum of date, invoice number, supplier and description of works undertaken. - Does the amount in the general ledger reconcile with the amount lodged in the CMS, the V Form C-IR and the DEC form? (If the evidence of expenditure differs from the amount claimed, a reconciliation statements needs to be provided). - Does the general ledger/transaction report provide sufficient information on all expenditure being claimed within a specific financial year, and include the date that expenditure was posted in the general ledger? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 22b) | - Invoices/Purchase orders and all relevant Contracts: - Must be verified against all works undertaken. - All invoices must correlate to general ledger/transaction listing - All reconstruction works were undertaken within a specific financial year, prior to the end of the allowable time period - All invoices have been provided by the Delivery Agency i.e. if the claim comprises of 10 invoices, that 10 invoices have been provided. - Do the invoices provide adequate detail to show what works were undertaken and how line item value has been determined? - Is any supporting information required to substantiate claim value? Has this been provided? - Does invoice indicate date of works? Does this fall within allowable time period? - Does invoice description adequately connect expenditure to event, asset, Dates of works and eligible damage repair? - Do overall invoice values match claim values and transaction listing values? - Have any invoices been over claimed, duplicated in current or previous claims? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 22c) | - Payroll costs: - Payroll costs must correlate to general ledger/transaction listing. - Has the Delivery Agency provided payroll reports for extraordinary payroll costs (overtime) and evidence of the additional resources required? Timesheets to be available for sampling upon request. - Where a position description has been approved by the Administering Authority for particular role/s, has this also been provided as part of the claim and supported by relevant payroll reports? Note approved roles must only correlate to works being undertaken 1 week post the disaster. | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 22d) | - Quarterly Progress reporting: - Has the Delivery Agency provided quarterly progress reporting to the Assessing Authority? - If not, Delivery Agency is required to provide a quarterly progress report for this Works Package prior to this claim being assessed. - Does the quarterly progress report/s correlate to C-RW and C-CW forms? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 23 | Project Accounting (DRFA Objective C5 DRFA Clause No. 7.1.9) - Is the expenditure allocated to the correct essential public asset (YTD actual/certified estimate) - Has a breakdown of the indirect costs, contingency and cost escalation been provided? - Where project contingency has been used, is it within the approved project scope and appropriately detailed as to the reason the project contingency was used. - Provide commentary where actual costs are far less or exceed the certified estimate? Where costs exceed the certified estimate, has the Delivery Agency advised the Assessing Authority formally of this overspend including the reasons for the variation as soon as practically possible? Has the Assessing Authority also advised formally of the overspend to determine if an Independent Technical Reviewer be engaged under Section 8 of the DRFA and an independent review of an asset undertaken as per Applications 1-3 under clause 8.1 of the DRFA? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 24 | Procurement Practices (DRFA Objective C4 DRFA Clause No. 6.4.6) Has the Assessing Authority checked that the Delivery Agency complied with the procurement policy and conveyed any concerns to the Administering Authority for a further consideration? Based on the size of the certified estimates package and or other intelligence on the Delivery Agency, i.e., has been placed into administration by the Victorian Local Government Minister for issues associated with financial and/or governance concerns, where requested by the Administering Authority, has the Delivery Agency provided a Delivery Agency Internal Audit function attesting compliance of their procurement practices. | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 25 | Supporting documentation Have all supporting documentation provided in the CMS by the Delivery Agency been structured as per the following: - Damage sub folder - Pre-condition sub folder - Pre-condition reports – signed - Inspection - Estimate - Post-completion works sub folder for the claim no. associated with this validation process | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 26 | Photo report – Works Undertaken (DRFA Objective D3.1, 3.2, D5.1, D5.2, DRFA Clause 6.1, 6.2) - Has the Delivery Agency now provided a completed photo report for reconstruction works undertaken and their locations (latitude and longitude) - Have they capture the date photos were taken? - Are the photos presented in a logical sequence for each asset with asset name and reference number (where available)? - Do the photos provide representative evidence of each of the key treatments undertaken on an asset? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 27 | Photo report – Sample review (DRFA Objective D3.1, 3.2, D5.1, D5.2, DRFA Clause 6.1, 6.2) - Has the Assessing Authority undertaken a sample review of the photo reports and provided commentary in this checklist and/or an attachment outlining the sampling approach including sample size undertaken and the photos reviewed as well as the outcome of the sampling? - Sampling needs to include a review of the geospatial locations (i.e., latitude and longitude) provided in the photo reports against the meta data in the separate photo files i.e., jpg as well as any software used by the Delivery Agency that captures this actual data, to ensure that works is associated with the correct asset. | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 28 | Photos (DRFA Objective D3.1, 3.2, D5.1, D5.2, DRFA Clause 6.1, 6.2) - Has the Delivery Agency provided photo files with meta data intact and time taken? - Are the photo files grouped by asset and referenced uniquely? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 29 | Site inspections - Have site inspections been undertaken on a regular basis by the Assessing Authority? Please provide details below regarding the dates and locations of the site inspections: i.e., 00/00/0000 Smith Street Goonawarra - Have detailed site inspection notes been prepared including a list of those assets inspected? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 30 | Completed works: - Is the nature of the works undertaken eligible to be claimed under an essential public asset reconstruction works claim and are the works consistent to what has been approved as part of the Works Estimate Package? - Have the works been completed, and expenditure incurred within the allowable time period? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 31 | Key issues: Have key issues been brought to the attention of the Administering Authority and resolved and appropriately documented? | Y ☐; N ☐; N/A ☐. | Y ☐; N ☐; N/A ☐. |
| 32 | Identification of conflict-of-interest risk I have considered the nature of this task, considered my professional duties and personal interests and declare that, to the best of my knowledge no actual, potential or perceived conflict risk of exists in the assessment of this claim. Where an actual, potential or perceived risk is identified, detail of risk along with mitigation measures are to be identified. NOTE: Potential or perceived risk identified as result of being a rate payer in subject Delivery Agency may be sufficiently mitigated through disinterested party review of assessment to ensure impartiality. | ☐ No risk identified. ☐ Risk identified. Detail:. Mitigation:. | ☐ No risk identified. ☐ Risk identified. Detail:. Mitigation:. |
| 33 | Other Notes from Assessor ## Input feedback if required General Feedback for Delivery Agency ## Input feedback if required |  |  |

Assessing Authority Officer Declaration:

I hereby declare that the claim has been assessed for completeness and accuracy.

Signed:

Date:

Administering Authority Officer Declaration:

I hereby declare that the claim has been assessed for completeness and accuracy.

Signed:

Date: